## TASK LIST
M | Scrum master email | Scrum master ID | Date
Gengyi Sun | gengyi.sun@mail.mcgill.ca | 260768270 | 3.07
STORY | TASK | EFFORT ESTIMATE (hrs) | SPRINT | WHO | START DATE | END DATE | ACTUAL EFFORT (hrs) | STATUS
Story unrelated tasks | Weekly meetings (30 minutes per week) (scrums) | 0.5 | 1 | Gengyi Sun | 2021-02-16 | 2021-02-16 | 0 | DONE
| Task list preparation | 3 | 1 | Gengyi Sun | 2021-02-16 | 2021-03-07 | 1.5 | DONE
| Update backlogs | 1 | 1 | Gengyi Sun | 2021-02-16 | 2021-03-07 | 0.5 | DONE
| Testing videos | 1 | 1 | Gengyi Sun | 2021-03-07 | 2021-03-07 | 1.5 | DONE
S1 | Add new user | 1 | 1 | Gengyi Sun | 2021-01-27 | 2021-02-14 | 1 | DONE
(8 points) | Desgin the model for the user objects | 2 | 1 | Gengyi Sun | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controllers and define APIs to interact with user attributes | 1 | 1 | Gengyi Sun | 2021-01-27 | 2021-02-14 | 2 | DONE
| Implement dao and dto for the User class | 2 | 1 | Gengyi Sun | 2021-01-27 | 2021-02-14 | 2 | DONE
| Implement interfaces to register a new user | 2 | 2 |  |  |  |  | TO DO
| Test if the new user will be created in the database | 2 | 1 | Gengyi Sun | 2021-01-27 | 2021-02-07 | 3 | DONE
| Implement the JUnit test | 4 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-07 | 4 | DONE
| Test if the new user can log in the system | 2 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-07 | 2 | DONE
Total for S1 | 16
S3 | Change user attributes | 1 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-14 | 1 | DONE
(4 points) | Desgin the model for the user objects | 2 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement the corresponding funtion in Controller | 3 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controllers and define APIs to interact with user attributes | 2 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement interfaces to access user attributes | 2 | 2 |  |  |  |  | TO DO
| Integrate the interface with backend APIs | 2 | 2 |  |  |  |  | TO DO
| Test if the user attributes can be created or updated | 2 | 1 | Yinuo Wang | 2021-01-27 | 2021-02-07 | 2 | DONE
| Implement the JUnit test | 4 | 1 | Hao Shu | 2021-01-27 | 2021-02-07 | 4 | DONE
| Test if user's attribute is changed in databse when | 2 | 1 | Hao Shu | 2021-01-27 | 2021-02-07 | 3 | DONE
Total for S3 | 20
S8 | Query user list | 1 | 1 | Hao Shu | 2021-01-27 | 2021-02-14 | 1 | DONE
(3 points) | Create transfer object holding informations to display | 2 | 1 | Hao Shu | 2021-01-27 | 2021-02-14 | 0.5 | DONE
| Implement the corresponding funtion in Controller | 3 | 1 | Hao Shu | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controller to communicate with the database | 2 | 1 | Hao Shu | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement a list-like display section on frontend | 2 | 2 |  |  |  |  | TO DO
| Implement a requesting interface which triggers the retrieving process | 2 | 2 |  |  |  |  | TO DO
| Test if the system is returning a list of users | 2 | 1 | Yuelin Liu | 2021-01-27 | 2021-02-07 | 2 | DONE
| Implement the JUnit test | 4 | 1 | Xiangyu Li | 2021-01-27 | 2021-02-07 | 4 | DONE
| Test if button on the frontend could bring out user list and display them | 1 | 1 | Xiangyu Li | 2021-01-27 | 2021-02-07 | 1 | DONE
Total for S8 | 19
S9 | Query user attributes | 1 | 1 | Xinran Li | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement the corresponding funtion in Controller | 3 | 1 | Xiangyu Li | 2021-01-27 | 2021-02-14 | 2 | DONE
(2 points) | Create transfer | 2 | 1 | Yuelin Liu | 2021-01-27 | 2021-02-14 | 2 | DONE
| Implement a list-like display section on frontend | 2 | 2 |  |  |  |  | TO DO
| Implememt a category interface to select sorting condition | 2 | 2 |  |  |  |  | TO DO
| Test if the system can return a list of users | 2 | 1 | Xinran Li | 2021-01-27 | 2021-02-07 | 2 | DONE
| Test if the return user list are sorted with the certain user attributes | 1 | 1 | Xinran Li | 2021-01-27 | 2021-02-07 | 1 | DONE
Total for S9 | 13
S25 | Create an advertisement | 1 | 1 | Xinran Li | 2021-01-27 | 2021-02-14 | 2 | DONE
(6 points) | Desgin the model for the advertisement objects | 2 | 1 | Xinran Li | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controllers and define APIs to interact with advertisement | 3 | 1 | Xinran Li | 2021-01-27 | 2021-02-14 | 3 | DONE
| Implement user interface to display and edit advertisements | 2 | 2 |  |  |  |  | TO DO
| Integrate the interface with backend APIs for advertisements | 3 | 2 |  |  |  |  | TO DO
| Test if an advertisement can be successfuly created | 2 | 1 | Yuelin Liu | 2021-01-27 | 2021-02-07 | 2 | DONE
| Test if an advertisement can be successfuly deleted | 1 | 1 | Linpei Duan | 2021-01-27 | 2021-02-07 | 1 | DONE
| Test if an advertisement can be disabled | 2 | 1 | Linpei Duan | 2021-01-27 | 2021-02-07 | 3 | DONE
| Test if an advertisement can be successfuly edited | 2 | 1 | Linpei Duan | 2021-01-27 | 2021-02-07 | 2 | DONE
Total for S25 | 18
S48 | Create customer service request | 1 | 1 | Linpei Duan | 2021-01-27 | 2021-02-14 | 1 | DONE
(2 points) | Desgin the model for the service request objects | 2 | 1 | Linpei Duan | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controllers and define APIs to interact with service requests | 2 | 1 | Chang Zhou | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement interface to track the status of the customer service | 2 | 2 |  |  |  |  | TO DO
| Integrate the interface with backend APIs for customer service request information (id, status, content) | 3 | 2 |  |  |  |  | TO DO
| Test if a service request can be successfuly created | 2 | 1 | Chang Zhou | 2021-01-27 | 2021-02-07 | 2 | DONE
| Implement the stepdefition and JUnit Test | 4 | 1 | Chang Zhou | 2021-01-27 | 2021-02-07 | 3 | DONE
| Test if a service request can be successfuly interacted with users (reply to the request, edit the request) | 2 | 1 | Chang Zhou | 2021-01-27 | 2021-02-07 | 2 | DONE
Total for S48 | 18
S54 | Send bitcoin from website | 1 | 1 | Amelia Cui | 2021-01-27 | 2021-02-14 | 2 | DONE
(3 points) | Implement Wallet Attribute for user objects | 2 | 1 | Amelia Cui | 2021-01-27 | 2021-02-14 | 1 | DONE
| Implement controller and define API to interact with the wallet | 2 | 1 | Amelia Cui | 2021-01-27 | 2021-02-14 | 2 | DONE
| Connect a frontline web to interact with the API | 3 | 2 |  |  |  |  | TO DO
| Pass the Gherkin scenrio test for backend | 2 | 1 | Amelia Cui | 2021-01-27 | 2021-02-07 | 2 | DONE
| Pass the integrated test | 2 | 1 | Amelia Cui | 2021-01-27 | 2021-02-05 | 2 | DONE
| Implement the JUnit test | 4 | 1 | Zeyang Xu | 2021-01-27 | 2021-02-07 | 4 | DONE
Total for S54 | 16
S55 | Receive bitcoin in website | 1 | 1 | Zeyang Xu | 2021-01-27 | 2021-02-14 | 1 | DONE
(3 points) | Generate the model for the bnitcoin trasaction. | 2 | 1 | Zeyang Xu | 2021-01-27 | 2021-02-14 | 1 | DONE
| Connect to a database. | 3 | 1 | Zeyang Xu | 2021-01-27 | 2021-02-14 | 2 | DONE
| Print the amount in the wallet. | 2 | 2 |  |  |  |  | TO DO
| Create the pop-up error hint | 3 | 2 |  |  |  |  | TO DO
| Test if the wallet amount will increase when receive bitcoin. | 2 | 1 | Yuankang Wei | 2021-01-27 | 07-02-2021 | 4 | DONE
| Implement the JUnit test | 4 | 1 | Gengyi Sun | 2021-01-27 | 07-02-2021 | 4 | DONE
| Test if the wallet amount will remain unchanged for an illegal trasaction. | 2 | 1 | Yuankang Wei | 2021-01-27 | 07-02-2021 | 4 | DONE
Total for S55 | 19
S2 | Remove existing user | 1 | 1 | Kaicheng Wu | 2021-01-27 | 2021-02-14 | 2 | DONE
(1 point) | Implement the funtions in Controller class | 3 | 1 | Kaicheng Wu | 2021-01-27 | 07-02-2021 | 2 | DONE
| Connect to a database. | 2 | 1 | Kaicheng Wu | 2021-01-27 | 2021-02-14 | 1.5 | DONE
| Create the pop-up error hint | 3 | 2 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 1 | Kaicheng Wu | 2021-01-27 |  |  | IN PROGRESS
| Test if the user could be removed | 2 | 1 | Kaicheng Wu | 2021-01-27 | 07-02-2021 | 2 | DONE
Total for S2 | 14.5
S4 | Change user credential (Feature file) | 2 | 2 | Xiangyu Li | 19-02-2021 | 20-02-2021 | 2 | DONE
(6 point) | Implement the funtions in Controller class | 1 | 2 | Xiangyu Li | 2021-02-19 | 21-20-2021 | 1 | DONE
| Implement safty mesures in Controller class | 2 | 2 | Xinran Li | 2021-02-22 | 27-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Xinran Li | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up error hint | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Xinran Li | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if the user's credentiala can be changed | 2 | 2 |  |  |  |  | TO DO
Total for S4 | 15.5
S26 | Edit an advertisement | 2 | 2 | Chang Zhou | 19-02-2021 | 20-02-2021 | 2.5 | DONE
(5 point) | Implement the funtions in Controller class | 3 | 2 | Chang Zhou | 2021-02-19 | 27-02-2021 | 3 | DONE
| Connect to a database. | 2 | 2 | Chang Zhou | 2021-02-19 | 27-02-2021 | 1 | DONE
| Create the pop-up successful message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Gengyi Sun | 07-03-2021 |  |  | IN PROGRESS
| Test the edit service request functions | 2 | 2 |  |  |  |  | TO DO
| Test if the advertisement content is changed | 2 | 2 |  |  |  |  | TO DO
Total for S26 | 17.5
S27 | Disable an advertisement | 2 | 2 | Hao Shu | 19-02-2021 | 20-02-2021 | 2 | DONE
(3 point) | Implement the funtions in Controller class | 3 | 2 | Zeyang Xu | 2021-02-22 | 26-02-2021 | 3 | DONE
| Connect to a database. | 2 | 2 | Zeyang Xu | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Zeyang Xu | 07-03-2021 |  |  | IN PROGRESS
| Test if the ads can be disabled | 2 | 2 |  |  |  |  | TO DO
Total for S27 | 15.5
S28 | Disable all advertisement | 2 | 2 | Yuelin Liu | 19-02-2021 | 20-02-2021 | 2 | DONE
(3 point) | Implement the funtions in Controller class | 3 | 2 | Linpei Duan | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Linpei Duan | 2021-02-22 | 26-02-2021 | 2 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Yuelin Liu | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if all ads are disabled | 2 | 2 | Yuelin Liu | 07-03-2021 |  |  | IN PROGRESS
Total for S28 | 15.5
S29 | Disable all selling advertisments | 2 | 2 | Kaicheng Wu | 19-02-2021 | 20-02-2021 | 2 | DONE
(3 point) | Implement the funtions in Controller class | 3 | 2 | Linpei Duan | 2021-02-22 | 07-03-2021 | 3 | DONE
| Connect to a database. | 2 | 2 | Linpei Duan | 2021-02-22 | 07-03-2021 | 2 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Linpei Duan | 2021-02-22 | 07-03-2021 | 3.5 | DONE
| Test if the selling ads are disabled | 2 | 2 | Linpei Duan | 07-03-2021 |  |  | IN PROGRESS
Total for S29 | 15.5
S30 | Disable all buying advertisement | 2 | 2 | Zeyang Xu | 19-02-2021 | 20-02-2021 | 2 | DONE
(3 point) | Implement the funtions in Controller class | 3 | 2 | Yuankang Wei | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Yuankang Wei | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Yuankang Wei | 2021-02-22 | 07-03-2021 | 3.5 | DONE
| Test if all buying ads are diabled | 2 | 2 | Yuankang Wei | 07-03-2021 |  |  | IN PROGRESS
Total for S30 | 15.5
S31 | Activate an advertisement | 2 | 2 | Amelia Cui | 19-02-2021 | 20-02-2021 | 2 | DONE
(5 point) | Implement the funtions in Controller class | 3 | 2 | Chang Zhou | 2021-02-22 | 07-03-2021 | 3 | DONE
| Connect to a database. | 2 | 2 | Chang Zhou | 2021-02-22 | 07-03-2021 | 2 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Chang Zhou | 2021-02-22 |  |  | IN PROGRESS
| Test if the ads is activated | 2 | 2 | Chang Zhou | 07-03-2021 |  |  | IN PROGRESS
Total for S31 | 15.5
S32 | Activate all advertisement | 2 | 2 | Gengyi Sun | 19-02-2021 | 20-02-2021 | 2 | DONE
(5 point) | Implement the funtions in Controller class | 3 | 2 | Zeyang Xu | 2021-02-22 | 27-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Zeyang Xu | 2021-02-22 | 28-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Zeyang Xu | 2021-02-22 | 07-03-2021 | 3.5 | DONE
| Test if all ads are activated | 2 | 2 | Zeyang Xu | 07-03-2021 |  |  | IN PROGRESS
Total for S32 | 15.5
S33 | Activate all selling advertisement | 2 | 2 | Xinran Li | 19-02-2021 | 20-02-2021 | 2 | DONE
(5 point) | Implement the funtions in Controller class | 3 | 2 | Kaicheng Wu | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Kaicheng Wu | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Kaicheng Wu | 2021-02-22 | 07-03-2021 | 3.5 | DONE
| Test if all the selling ads are activated | 2 | 2 | Kaicheng Wu | 07-03-2021 |  |  | IN PROGRESS
Total for S33 | 15.5
S34 | Activate all buying advertisement | 2 | 2 | Yinuo Wang | 19-02-2021 | 20-02-2021 | 2 | DONE
(5 point) | Implement the funtions in Controller class | 3 | 2 | Yinuo Wang | 19-02-2021 | 27-02-2021 | 3 | DONE
| Connect to a database. | 2 | 2 | Kaicheng Wu | 2021-02-22 | 07-03-2021 | 2 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Yinuo Wang | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if all buying ads are activated | 2 | 2 | Yinuo Wang | 07-03-2021 |  |  | IN PROGRESS
Total for S34 | 15.5
S35 | Cancel an advertisement | 2 | 2 | Yuankang Wei | 19-02-2021 | 20-02-2021 | 2 | DONE
(3 point) | Implement the funtions in Controller class | 3 | 2 | Amelia Cui | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Amelia Cui | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Amelia Cui | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if the ads is cancelled | 2 | 2 | Amelia Cui | 07-03-2021 |  |  | IN PROGRESS
Total for S35 | 15.5
S36 | Open a trade | 2 | 2 | Linpei Duan | 19-02-2021 | 20-02-2021 | 2 | DONE
(6 point) | Implement the funtions in Controller class | 3 | 2 | Yuelin Liu | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Amelia Cui | 2021-02-22 | 07-03-2021 | 2 | DONE
| Create the trade information UI page | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Yuelin Liu | 26-02-2021 |  |  | IN PROGRESS
| Test if the trade is open | 2 | 2 | Yuelin Liu | 26-02-2021 |  |  | IN PROGRESS
| Test if the trade contains the correct information | 2 | 2 |  |  |  |  | TO DO
Total for S36 | 17.5
S37 | Complete a trade | 2 | 2 | Yuankang Wei | 19-02-2021 | 20-02-2021 | 2 | DONE
(6 point) | Implement the funtions in Controller class | 3 | 2 | Hao Shu | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Hao Shu | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Hao Shu | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if the trade can be completed | 2 | 2 | Hao Shu | 07-03-2021 |  |  | IN PROGRESS
Total for S37 | 15.5
S38 | Cancel a trade | 2 | 2 | Yinuo Wang | 19-02-2021 | 20-02-2021 | 2 | DONE
(2 point) | Implement the funtions in Controller class | 3 | 2 | Xiangyu Li | 2021-02-22 | 26-02-2021 | 2.5 | DONE
| Connect to a database. | 2 | 2 | Xiangyu Li | 2021-02-22 | 27-02-2021 | 1.5 | DONE
| Create the pop-up message | 3 | 3 |  |  |  |  | TO DO
| Implement the JUnit test | 3.5 | 2 | Xiangyu Li | 26-02-2021 | 07-03-2021 | 3.5 | DONE
| Test if the trade can be cancelled | 2 | 2 | Xiangyu Li | 07-03-2021 |  |  | IN PROGRESS
Total for S37 | 15.5
Total for Sprint 2 | 221 | all work during S2)
Total hours planned: | 380
TO DO | 87
DONE | 253.5
IN PROGRESS | 39.5
TIMESHEET | Total time (actual time) | (last+this week)
Kaicheng Wu | 9.5
Hao Shu | 9.5
Yuankang Wei | 11.5
Yinuo Wang | 10.5
Zeyang Xu | 9.5
Amelia Cui | 9.5
Chang Zhou | 11.5
Yuelin Liu | 10
Gengyi Sun | 9.5
Linpei Duan | 11.5
Xinran Li | 9.5
Xiangyu Li | 10.5
Legend:
STATUS
TO DO
IN PROGRESS
DONE
CATEGORY
DOCUMENTATION/GHERKINS
TESTING
BACKEND
FRONTEND

## BURNDOWN CHART
Sprint 3 | Burndown chart
DATA:
Week # | Story points
0 | 30
1 | 30
2 | 35
3 | 19