## 工作表1
Identifier | Name | Point | Priority | Refinement State | Detail in file
ID001 | Add new user | 8 | Implemented(8 points) | Groomed | ID001_Add_new_user
ID002 | Remove existing user | 1 | Implemented (1 point) | Groomed | ID002_Remove_existing_user
ID003 | Change user attributes | 4 | Implemented(4 points) | Groomed | ID003_Change_user_attributes
ID004 | Change user credential | 6 | Implemented (1 point) | Groomed | ID004_Change_user_credential
ID005 | Lock an existing user | 1 | Implement in the next future sprint | Groomed | ID005_Lock_user
ID006 | Unlock an existing user | 1 | Implement in the next future sprint | Groomed | ID006_Unlock_user
ID007 | Change user credit | 2 | Implement in the next future sprint | Groomed | ID007_Change_user_credit
ID008 | Query user list | 3 | Implemented (3 points) | Groomed | ID008_Query_user_list
ID009 | Query user attributes | 2 | Implemented(2 points) | Groomed | ID009_Query_user_attributes
ID010 | Query account balance | 2 | Implement in the next future sprint | Groomed | ID010_Query_account_balance
ID011 | Query user credit | 2 | Implement in the next future sprint | Groomed | ID011_Query_user_credit
ID012 | Query user status | 2 | Implement in the next future sprint | Groomed | ID012_Query_user_status
ID013 | Query user encrypted credential | 2 | Implement in the next future sprint | Groomed | ID013_Query_user_encrypted_credential
ID014 | Query users system usage |  | Implement in some future sprint | Not Groomed
ID015 | Full Backup of system |  | Implement in some future sprint | Not Groomed
ID016 | Restore full backup |  | Implement in some future sprint | Not Groomed
ID017 | Data integrity check |  | Implement in some future sprint | Not Groomed
ID018 | Reset system |  | Implement in some future sprint | Not Groomed
ID019 | Install patch |  | Implement in some future sprint | Groomed | ID019_Install_Patch
ID020 | Remove patch |  | Implement in some future sprint | Groomed | ID020_Remove_Patch
ID021 | Define active trading time for system |  | Implement in some future sprint | Groomed | ID021_Define_Active_Trading_Time
ID022 | Generate transaction summary report |  | Implement in some future sprint | Groomed | ID022_Generate_Transcation_Summary
ID023 | Generate user summary report |  | Implement in some future sprint | Groomed | ID023_Generate_User_Summary
ID024 | Generate user change summary report |  | Implement in some future sprint | Groomed | ID024_Generate_User_Change_Summary
ID025 | Create an advertisement | 6 | Implemented (6 points) | Groomed | ID025_Create_an_advertisement
ID026 | Edit an advertisement | 5 | Implemented (5 point) | Groomed | ID026_Edit_an_advertsement
ID027 | Disable an advertisement | 3 | Implemented (3 point) | Groomed | ID027_Disable_an_advertisement
ID028 | Disable all advertisements | 3 | Implemented (3 point) | Groomed | ID028_Disable_all_advertisements
ID029 | Disable all selling advertisements | 3 | Implemented (3 point) | Groomed | ID029_Disable_all_selling_advertisements
ID030 | Disable all buying advertisements | 3 | Implemented (3 point) | Groomed | ID030_Disable_all_buying_advertisements
ID031 | Activate an advertisement | 5 | Implemented (5 point) | Groomed | ID031_Activate_an_advertisement
ID032 | Activate all advertisements | 5 | Implemented (5 point) | Groomed | ID032_Activate_all_advertisements
ID033 | Activate all selling advertisements | 5 | Implemented (5 point) | Groomed | ID033_Activate_all_selling_advertisements
ID034 | Activate all buying advertisements | 5 | Implemented (5 point) | Groomed | ID034_Activate_all_buying_advertisements
ID035 | Cancel an advertisement | 3 | Implemented (3 point) | Groomed | ID035_Cancel_an_advertisement
ID036 | Open a trade | 6 | Implemented (6 point) | Groomed | ID036_Open_a_trade
ID037 | Complete a trade | 6 | Implemented (6 point) | Groomed | ID037_Complete_a_trade
ID038 | Cancel a trade | 2 | Implemented (2 point) | Groomed | ID038_Cancel_a_trade
ID039 | Query cancelled trades | 4 | Implement in the next future sprint | Groomed | ID039_Query_cancelled_trades
ID040 | Query completed trades | 4 | Implement in the next future sprint | Groomed | ID040_Query_completed_trades
ID041 | Query on-going trade | 4 | Implement in the next future sprint | Groomed | ID041_Query_ongoing_trade
ID042 | Query cancelled advertisement | 4 | Implement in the next future sprint | Groomed | ID042_Query_cancelled_advertisement
ID043 | Query completed advertisement | 4 | Implement in the next future sprint | Groomed | ID043_Query_completed_advertisement
ID044 | Query on-going advertisement | 4 | Implement in the next future sprint | Groomed | ID044_Query_ongoing_advertisement
ID045 | Update user's trading limit Tier | 4 | Implement in the next future sprint | Groomed | ID045_Update_user_trading_limit_Tier
ID046 | Provide feedback for user's trade | 4 | Implement in the next future sprint | Groomed | ID046_Provide_feedback_for_user_trade
ID047 | Update user's feedback score | 4 | Implement in the next future sprint | Groomed | ID047_Update_user_feedback_score
ID048 | Create customer service request | 2 | Implemented (2 points) | Groomed | ID048_Create_customer_service_request
ID049 | Responde to customer service |  | Implement in some future sprint | Not Groomed
ID050 | Query requests |  | Implement in some future sprint | Not Groomed
ID051 | Link an email to user account | 3 | Implement in the next future sprint | Groomed | ID051_Link_an_email_to_user_account
ID052 | Manage user email contact | 3 | Implement in the next future sprint | Groomed | ID052_Manage_user_email_contact
ID053 | Send verification email to user |  | Implement in some future sprint | Not Groomed
ID054 | Send bicoin from website | 3 | Implemented (3 points) | Groomed | ID054_Transfer_Bitcoin_from_app
ID055 | Receive bitocin in website | 3 | Implementedt (3 points) | Groomed | ID055_Transfer_Bitcoin_to_app
ID056 | Display bitcoin exchange rate |  | Implement in some future sprint | Not Groomed
ID057 | Display individual daily earning |  | Implement in some future sprint | Not Groomed
ID058 | Display trade advertisement |  | Implement in some future sprint | Not Groomed
ID059 | Monitor exchange rate |  | Implement in some future sprint | Not Groomed
ID060 | Monitor bitcoin mining rate |  | Implement in some future sprint | Not Groomed
ID061 | Monitor bitcoin storage |  | Implement in some future sprint | Not Groomed